## EXAMPLE Project Portfolio Gantt
Project Portfolio Gantt Chart Template Example
START DATE
2025-01-01
[5 empty] | YEAR ONE | [11 empty] | YEAR TWO | [11 empty] | YEAR THREE | [11 empty] | DO NOT ALTER CELL BELOW
[5 empty] | Y1Q1 |  |  | Y1Q2 |  |  | Y1Q3 |  |  | Y1Q4 |  |  | Y2Q1 |  |  | Y2Q2 |  |  | Y2Q3 |  |  | Y2Q4 |  |  | Y3Q1 |  |  | Y3Q2 |  |  | Y3Q3 |  |  | Y3Q4
Projects | Status | Start Date | End Date | # of Days | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01
Project 1 | Complete | 2025-01-05 | 2025-05-05 | 86 | bar: 2025-01-01 to 2025-05-01
Project 2 | In Progress | 2025-04-02 | 2025-08-31 | 108 | bar: 2025-04-01 to 2025-08-01
Project 3 | On Hold | 2025-07-11 | 2025-10-15 | 69 | bar: 2025-07-01 to 2025-10-01
Project 4 | Overdue | 2025-10-01 | 2025-12-31 | 66 | bar: 2025-10-01 to 2025-12-01
Project 5 | Needs Review | 2026-01-05 | 2026-03-11 | 48 | bar: 2026-01-01 to 2026-03-01
Project 6 | Scheduled | 2026-03-12 | 2026-04-21 | 29 | bar: 2026-03-01 to 2026-04-01
Project 7 |  | 2025-04-22 | 2025-09-21 | 109 | bar: 2025-04-01 to 2025-09-01
Project 8 |  | 2025-05-30 | 2025-11-02 | 111 | bar: 2025-05-01 to 2025-11-01
Project 9 |  | 2025-08-05 | 2025-12-19 | 99 | bar: 2025-08-01 to 2025-12-01
Project 10 |  | 2025-10-25 | 2025-10-31 | 5 | bar: 2025-10-01
Project 11 |  | 2025-10-25 | 2026-03-26 | 109 | bar: 2025-10-01 to 2026-03-01
Project 12 |  | 2025-12-01 | 2026-08-15 | 185 | bar: 2025-12-01 to 2026-08-01
Project 13 |  | 2026-02-14 | 2026-02-28 | 10 | bar: 2026-02-01
Project 14 |  | 2026-02-28 | 2026-06-28 | 85 | bar: 2026-02-01 to 2026-06-01
Project 15 |  | 2026-03-02 | 2026-06-28 | 85 | bar: 2026-03-01 to 2026-06-01
Project 16 |  | 2026-06-28 | 2026-07-11 | 10 | bar: 2026-06-01 to 2026-07-01
Project 17 |  | 2026-07-14 | 2026-09-27 | 54 | bar: 2026-07-01 to 2026-09-01
Project 18 |  | 2026-10-01 | 2027-02-28 | 107 | bar: 2026-10-01 to 2027-02-01
Project 19 |  | 2026-12-01 | 2027-02-28 | 64 | bar: 2026-12-01 to 2027-02-01
Project 20 |  | 2027-01-01 | 2027-03-31 | 64 | bar: 2027-01-01 to 2027-03-01
Project 21 |  | 2027-03-25 | 2027-07-01 | 71 | bar: 2027-03-01 to 2027-07-01
Project 22 |  |  |  | 0
Project 23 |  |  |  | 0
Project 24 |  |  |  | 0
Project 25 |  |  |  | 0
Project 26 |  |  |  | 0
Project 27 |  |  |  | 0
Project 28 |  |  |  | 0
Project 29 |  |  |  | 0
Project 30 |  |  |  | 0
CLICK HERE TO CREATE IN SMARTSHEET | bar: 2025-01-01 to 2025-12-01

## Timeline Gantt chart
SPRFMO 2ND PERFORMANCE REVIEW IMPLEMENTATION TIMELINE
START DATE
2026-03-01
[5 empty] | YEAR ONE (2026) | [11 empty] | YEAR TWO (2027) | [11 empty] | YEAR THREE (2028) | [11 empty] | YEAR FOUR (2029) | [11 empty] | YEAR FIVE (2030)
[5 empty] | Y1Q1 (COMM14) |  |  | Y1Q2 |  |  | Y1Q3 |  |  | Y1Q4 |  |  | Y2Q1 (COMM15) |  |  | Y2Q2 |  |  | Y2Q3 |  |  | Y2Q4 |  |  | Y3Q1 (COMM16) |  |  | Y3Q2 |  |  | Y3Q3 |  |  | Y3Q4 |  |  | Y3Q1 (COMM17) |  |  | Y3Q2 |  |  | Y3Q3 |  |  | Y3Q4 |  |  | Y3Q1 (COMM18) |  |  | Y3Q2 |  |  | Y3Q3 |  |  | Y3Q4
Projects | Priority level | Status | Start Date | End Date | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | 2028-07-01 | 2028-08-01 | 2028-09-01 | 2028-10-01 | 2028-11-01 | 2028-12-01 | 2029-01-01 | 2029-02-01 | 2029-03-01 | 2029-04-01 | 2029-05-01 | 2029-06-01 | 2029-07-01 | 2029-08-01 | 2029-09-01 | 2029-10-01 | 2029-11-01 | 2029-12-01 | 2030-01-01 | 2030-02-01 | 2030-03-01 | 2030-04-01 | 2030-05-01 | 2030-06-01 | 2030-07-01 | 2030-08-01 | 2030-09-01 | 2030-10-01 | 2030-11-01 | 2030-12-01 | 2031-01-01 | 2031-02-01
Rec 1 - Annual Strategic Discussion & Statement of Intent | Low | On Hold | 2027-03-01 | 2028-03-01 | [12 empty] | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 2 - Development of a 3‑Year Business Plan and Headquarters Agreement Review | High | Proposed | 2026-03-01 | 2028-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 3 - Improving Direction to Subsidiary Bodies & Secretariat (separate workplans and Secretariat Operational Plan) | Medium | Proposed | 2026-03-01 | 2028-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 4 - Recruitment of a Competent Executive Secretary | High (Ongoing) | In Progress | 2026-03-01 | 2029-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 5 - Independent Review of the Headquarters Agreement | Low | On Hold | 2028-03-01 | 2029-03-01 | [24 empty] | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 6 - Secretariat Business Plan (3‑Year Horizon) | High | Proposed | 2026-03-01 | 2028-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 7 - Develop an Information Management Strategy (IMS) & Data Management Plan (DMP) | High | In Progress | 2025-03-01 | 2028-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 8 - Elevate the Data Working Group | Medium | Needs Review | 2026-03-01 | 2027-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 9 - Comprehensive Review of CMM 02 (Data Standards) | High | Needs Review | 2026-03-01 | 2028-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 10 - Cooperation on Jack Mackerel Across Jurisdictions | Medium | Needs Review | 2026-03-01 | 2030-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 11 - Ecosystem and Bycatch Analysis for Jack Mackerel | Medium | In Progress | 2026-03-01 | 2030-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 12 - Squid MSE, HCR and Alternative Management Approaches | Medium | Needs Review | 2026-03-01 | 2030-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 13 - Data Sharing for Squid (Including National Jurisdictions) | High (Ongoing) | Needs Review | 2026-03-01 | 2030-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 14 - Increased Observer Coverage in Squid | Medium | Needs Review | 2029-03-01 | 2030-03-01 | [35 empty] | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 15 - Precautionary Squid Effort Limitations | Medium | Proposed | 2026-03-01 | 2029-01-03 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 16 - Funding for External Scientific Expertise (Squid) | Low (Ongoing) | Needs Review | 2026-03-01 | 2030-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 17 - Alternative Approaches for Deepwater Management | Medium | On Hold | 2027-03-01 | 2028-03-01 | [12 empty] | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 18 - Operational Triggers for Deepwater Species | Low (ongoing) | Needs Review | 2026-03-01 | 2030-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 19 - Framework for Transitioning Exploratory Fisheries | High | In Progress | 2026-03-01 | 2029-01-03 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 20 - Cumulative Impact Review of Exploratory Fisheries | Medium | On Hold | 2028-03-01 | 2029-03-01 | [24 empty] | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 21 - Strengthened RFMO Cooperation (especially CCAMLR) | Medium (ongoing) | In Progress | 2026-03-01 | 2030-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 22 - Harvest Strategy Framework for All Fisheries | High | Proposed | 2026-03-01 | 2029-01-03 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 23 - Elevation of Spanish as a Working Language | High | In Progress | 2025-03-01 | 2027-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 24 - Article 19 (Developing States) Implementation Plan | Medium | Needs Review | 2027-03-01 | 2028-03-01 | [12 empty] | A | A | A | A | A | A | A | A | A | A | A | A | A

## Annotated Timeline
Indicative timeline for recommendations | Priority | Has the work started? | 2026 | 2027 | 2028 | 2029 | 2030
Recommendation 1 - Annual Strategic Discussion & Statement of Intent | Low | No – needs COMM decision |  | COMM15 to consider a Statement of Intent and annual strategic discussion.
Recommendation 2 — Development of a 3‑Year Business Plan and HQA | High | No – needs COMM decision | COMM14 would need to agree to the Business Plan, and then agree to a timeline for the work to be carried out, and task the Plan to be developed internally or independently. | Draft brought to COMM15 as a working paper. Comments required by COMM15 and either agreed or tasked to continue to develop. | If not finished in 2027, brought forward to COMM16 in 2028 for agreement.
Recommendation 3 — Improving Direction to Subsidiary Bodies & Secretariat (separate workplans and Secretariat Operational Plan) | Medium | No– needs COMM decision | Commission to agree to separate workplans and Secretariat Operational Plan at COMM14 – subsidiary Chairs to work during the intersessional period. | Workplans and Operational Plan presented to COMM15 series of meetings. Comments required by COMM15 and either agreed or tasked to continue to develop. | Full workplans agreed by COMM16. Operational Plan to potentially coincide with development of SPRFMO Business Plan)
Recommendation 4 — Recruitment of a Competent Executive Secretary (High priority) | High | Yes | Performance review conducted annually. | Performance review conducted annually. | Performance review conducted annually. | This recommendation is assessed this year coinciding with the ES four-year term.
Recommendation 5 — Independent Review of the Headquarters Agreement | Low | No – needs COMM decision |  |  | If this rec is agreed, timeline will need to be determined. If agreed, suggest that discussions commence in 2028 noting the lower priority rating. | Independ work to occur in 2028 and brought forward to COMM17 for consideration.
Recommendation 6 — Secretariat Business Plan (3 Year Horizon) | High | No – needs COMM decision (as per rec 2) | COMM14 would need to agree to the Business Plan, and then agree to a timeline for the work to be carried out, and task the Plan to be developed internally or independently. | Draft brought to COMM15 as a working paper. Comments required by COMM15 and either agreed or tasked to continue to develop. | If not finished in 2027, brought forward to COMM16 in 2028 for agreement.
Recommendation 7 — Develop an Information Management Strategy (IMS) & Data Management Plan (DMP) | High | Yes | Commission to instruct subsidiaries to review the draft IMS and DMP. | IMS and DMP drafts brought to COMM15 series of meetings to be reviewed by subsidiaries and Commission. Potential to have these agreed at this meeting. | At the latest, final drafts brought forward to COMM16 for agreement.
Recommendation 8 — Elevate the Data Working Group | Medium | No – needs COMM decision | COMM14 to discuss/agree in principle. COMM may need to task the revision of DWG ToR. | Revised ToRs brought to COMM15 for agreement.
Recommendation 9 — Comprehensive Review of CMM 02 (Data Standards) | High | No – needs COMM decision | No – needs COMM decision | COMM14 may want to consider a review during the 2026 intersessional period, which will align with the IMS and DMP development timeline. | If 2026 intersessional work is agreed, review brought to COMM15 for consideration. | Amendments to CMM 02 proposed and implemented.
Recommendation 10 — Cooperation on Jack Mackerel Across Jurisdictions | Medium | No (but currently voluntary) | Needs review – COMM14/15 to confirm if the current data sharing and stock assessment work is not sufficient to achieve this recommendation. | If no, COMM15 discussion on ways to incentivise improved cooperation. | Any improvements noted at COMM16. | Any improvements noted at COMM17. | The completion of this recommendation is reviewed.
Recommendation 11 — Ecosystem and Bycatch Analysis for Jack Mackerel (Medium for Chubb Mackerel, low for other species) | Medium | Yes | Work planned for 2026 on chub mackerel bycatch. However, COMM will need to decide if a Commission would want SC to undertake a broader analysis on JM fishery impacts on other stocks and ecosystem impacts. | If yes, SC to bring forward a plan (develop into their workplan) for COMM consideration. | 2028 dependent on SC’s timeline. | 2029 dependent on SC’s timeline. Work potentially brought forward to SC16 and then to COMM17 for consideration. | Potential changes to CMM 01 to be considered/reviewed.
Recommendation 12 — Squid MSE, HCR and Alternative Management Approaches | Medium | No – needs COMM decision | MSE, HCR and alternative options to the stock assessment including their timing are already being considered as part of the SC multiannual workplan. COMM14 would need to consider these recommendations and provide a clear mandate to SC. | If mandate is given to SC, SC to advise on appropriate timeline. | Work continues | SC to provide advice to COMM17. COMM17 to review findings and consider current management and if changes need occur based on SC advice. | Changes brought forward as a proposal to COMM18.
Recommendation 13 — Data Sharing for Squid (Including National Jurisdictions) | High | No | Needs discussion at COMM on whether this is something SPRFMO and Members with squid fisheries in areas under national jurisdiction hope to achieve in the medium to long term. | If yes, then SC to instruct COMM on what data is needed to be able to facilitate assessments. COMM15 to consider ways to incentivise data sharing. | Ongoing. | Ongoing. | Ongoing.
Recommendation 14 — Increased Observer Coverage in Squid | Medium | No – not since the changes in 2023. |  |  |  | COMM to consider observer coverage requirements in 2029 to coincide with rec 12 management needs
Recommendation 15 — Precautionary Squid Effort Limitations | Medium | No | Note there is one proposal to COMM14 | COMM to review based on any new advice or proposals to COMM | COMM to review based on any new advice or proposals to COMM | COMM to consider effort limitations in 2029 to coincide with rec 12 and rec 14.
Recommendation 16 — Funding for External Scientific Expertise (Squid) | Low | No | Ongoing (case-by-case) | Ongoing (case-by-case) | Ongoing (case-by-case) | Ongoing (case-by-case) | Ongoing (case-by-case)
Recommendation 17 — Alternative Approaches for Deepwater Management | Medium | No – needs COMM decision | Post COMM15 (February 2027) | COMM to consider after the outcomes from the UN Bottom Fishing Review and UNGA. If review is agreed, progress during the 2027 intersessional. | Any amendments brought to COMM17.
Recommendation 18 — Operational Triggers for Deepwater Species | Low | Yes | Ongoing (case-by-case) | Ongoing (case-by-case) | Ongoing (case-by-case) | Ongoing (case-by-case) | Ongoing (case-by-case)
Recommendation 19 — Framework for Transitioning Exploratory Fisheries | High | Yes – since SC13 | Workshop to be held after SC14 (September 2026). | COMM15 to consider workshop recommendations. | New measure drafting. | New measure finalisation.
Recommendation 20 — Cumulative Impact Review of Exploratory Fisheries | Medium | No |  |  | Noting lower priority, to be considered in 2028 to make way for other high priority recs
Recommendation 21 — Strengthened RFMO Cooperation (especially CCAMLR) | Medium | Yes | Ongoing – each year this is reviewed and COMM Members are invited to comment. this rec could be integrated into the work under recommendation 19. | Ongoing – reviewed annually. Potential stocktake of new measures which SPRFMO has taken to increase cooperation. | Ongoing – reviewed annually. | Ongoing – reviewed annually. | Ongoing – reviewed annually.
Recommendation 22 — Harvest Strategy Framework for All Fisheries | High | No – needs COMM decision | Commission to agree to exploring a framework/and guide the work of the SC. | Harvest Strategy Framework development to occur. | Harvest Strategy Framework presented to COMM16 (2028) | Finalised by 2029.
Recommendation 23 — Elevation of Spanish as a Working Language | High | Yes | Already agreed – the Secretariat and FAC to continue work |  | Spanish language is elevated by COMM15 (2026) (dependent on plan which is being developed)
Recommendation 24 — Article 19 (Developing States) Implementation Plan | Medium | No – needs COMM decision |  | COMM15 to consider commissioning work to develop a draft plan | If agreed, draft plan brought to COMM16 as a working paper for comment and agreement.

## Status Keys - Do Not Delete
Status Key - Do Not Delete
STATUS KEY
Proposed
In Progress
Complete
On Hold
Overdue
Needs Review
Scheduled